## Iteration 3
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
3 | login.jsp | username and password displayed in URL [not POST] | low | Gao Shuang | 2015-10-07 | Solved | Fuyan | 2015-10-07 | Change form method to POST. So wrong user log in will not show details in URL.
3 | authenticate.jsp | Login using User Name: "Sean Tan" as username. | high | Gao Shuang | 2015-10-07 | Solved | Fuyan | 2015-10-07 | Change login username to verify email address

## Iteration 4
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
4 | authenticate.jsp | Login using email address "sean.tan.2014 @sis.smu.edu.sg" as username | High | Fu Yan | 2015-10-22 | Solved | Fu Yan | 2015-10-22 | Log in user name should not be full email address. Use email ID
4 | ProcessBasicAppUsage.java, processDiurnal.java, processAppCategory.java | Direct servlet access causes a NullPointerException | Critical | Fu Yan | 2015-10-22 | Solved | Claudie Ang | 2015-10-23
4 | BootstrapServlet.java UpdateServlet.java | Direct servlet access causes a NullPointerException | Critical | Fu Yan | 2015-10-22 | Solved | Wang MiaoQiong | 2015-10-23
4 | UserAppUsage.java | Basic app usage report does not calculate use time on a daily basis. For example: Timestamp1: 06-04-2015 23:59:58 Timestamp2: 07-04-2015 00:00:02 Daily basis, should be using 07-04-2015 00:00:00 as seperator and calculate 2 days seperatly instead if using timestamp2 minus timestamp1 | High | Claudie Ang | 2015-10-22 | Solved | Claudie Ang | 2015-10-23
4 | adminDisplay.java udpateDisplay.java | Bootstrap upload form cannot validate non-zip format files. Causing code running into servlet and generate NullPointerException | Critical | Claudie Ang | 2015-10-22 | Solved | Fu Yan | 2015-10-24
4 | BootstrapServlet.java UpdateServlet.java Unzip.java | Zip file uploaded containing irrelevant documents (e.g. pdf, word docs, excel…) is not ignored and unzipped into project directory. Reading these files in servlet will cause the application to be stuck on servlet page | Critical | Claudie Ang | 2015-10-22 | Solved | Fu Yan | 2015-10-25
4 | basicAppUsageReportDemo.jsp | NullPointerException if the filter (school, year, gender) dropdownlists are not selected | Critical | Claudie Ang | 2015-10-22 | Solved | Claudie Ang | 2015-10-25
4 | ProcessBasicAppUsage.java, BasicAppUsage.jsp, BasicAppUsageDemo.jsp, processDiurnal.java, processAppCategory.java | NullPointerException if no start date and end date values are entered | Critical | Claudie Ang | 2015-10-22 | Solved | Tian DeWang | 2015-10-25
5 | processBasicAppUsage.java, processTopkschools.java, processTopkstudents.java | Inputting startdate later than enddate does not produce an error message/ not validated | high | Claudie Ang | 2015-10-22 | Solved | Claudie Ang | 2015-10-25
5 | BootstrapServlet.java UpdateServlet.java | Without project cleanbuild, the data files unzipped need to be cleared manually | high | Claudie Ang | 2015-10-22 | Solved | Fu Yan | 2015-10-25

## Iteration 5
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
5 | BasicAppUsageDemo.jsp | Javascript error : allows same filter to be selected twice | low | Claudie Ang | 2015-11-03 | Solved | Claudie | 2015-11-04
5 | processAppCategory.java | Misspelled "Information" as "inforamtion": causes inaccurate results to be displayed | low | Claudie Ang | 2015-11-03 | Solved | Dewang | 2015-11-04
5 | processAppCategory.java; basicAppCategoryResult.jsp | Percentage values displayed has 2 decimal places | low | Claudie Ang | 2015-11-03 | Solved | Dewang | 2015-11-04
5 | adminDisplay.jsp | Header/Title displayed as "Samples : Simple Upload" | low | Claudie Ang | 2015-11-03 | Solved | Dewang | 2015-11-04
5 | topkAppUsageReport.java | submitting form without k-value and filter produces nullpointerexception | high | Claudie Ang | 2015-11-04 | Solved | Dewang | 2015-11-04
5 | smartphoneOverusageReport.jsp smartphoneOverusageResult.jsp | Protect page not included | high | Miaoqiong | 2015-11-04 | Solved | Tian Dewang | 2015-11-04
5 | smartphoneOverusageReport.jsp | "Start date cannot be earlier than end date", the error statement should be "End date cannot be earlier than start date | low | Claudie Ang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
5 | smartphoneOverusageReport.jsp smartphoneOverusageResult.jsp | Daily session calculation is done wrongly. The session should be seperated by every >= 120 seconds interval | low | Claudie Ang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
5 | BootstrapServlet.java UpdateServlet.java Unzip.java | A folder inside data zip file will cause servlet runtime exception | Critical | Claudie Ang | 2015-11-03 | Solved | Fu Yan | 2015-11-04
5 | BootstrapValidation.java | Bootstrap email should be case insensitive (SEAN.TAN.2015@SIS.SMU.EDU.SG) | low | Claudie Ang | 2015-11-03 | Solved | Fu Yan | 2015-11-04