## Overview
Overview of Bug metrics for all iterations
Iteration | Low | High | Critical | Total
3 | 13 | 7 | 1 | 58
4 | 19 | 1 | 2 | 44
5 | 19 | 10 | 1 | 79
6 (UAT Bug Logs) | 11 | 2 | 10 | 31

## Iteration 3
BUG LOG
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
3 | authenticate.jsp | Authentication returns false for all cases | low | Miaoqiong | 2015-09-28 | Solved | Miaoqiong | 2015-09-28
3 | UserDAO.java | Cannot load data | high | Gaoshuang | 2015-09-28 | Solved | Miaoqiong | 2015-09-28 | db.name in conection.properties did not match database name in myphpAdmin
3 | login.jsp | Error messages cannot be printed out | low | Miaoqiong | 2015-09-28 | Solved | Miaoqiong | 2015-09-28
3 | adminDisplay.jsp | Errror message cannot be printed when no file is chosen by user. | low | Claudie Ang | 2015-10-06 | Solved | Miaoqiong | 2015-10-06
3 | BootstrapValidation.java | Check app.csv duplicate row. Did not add header into arraylist to check for duplicated records. | low | Miaoqiong | 2015-10-06 | Solved | Gao Shuang | 2015-10-06 | Need to add at least 1 row of data into the arrayList to compare for duplicated rows.
3 | BootstrapValidation.java | Check invalid appid. Could not for alphabetical data. | low | Claudie Ang | 2015-10-06 | Solved | Fu Yan | 2015-10-06 | try and catch NumberFormatException.
3 | BootstrapValidation.java | Check duplicated rows. After boolean is "false", did not put "break;" | low | Claudie Ang | 2015-10-06 | Solved | Claudie Ang | 2015-10-06
3 | BootstrapValidation.java | "if" condition for checking duplicated rows does not work properly. "&&" "¦¦" | low | Claudie Ang | 2015-10-06 | Solved | Claudie Ang | 2015-10-06
3 | BootstrapValidation.java | Duplicated rows, after checking could not add correct rows into arraylist | high | Miaoqiong | 2015-10-06 | Solved | Fu Yan | 2015-10-06 | Add to validated arrayList outside of for loop.
3 | BootstrapValidation.java | Line Number could not be displayed properly | low | Miaoqiong | 2015-10-06 | Solved | Fu Yan | 2015-10-06 | Line Number ++ or -- after every check.
3 | Bootstrap.java and adminDisplay.jsp | Error messages cannot be forward to adminDisplay | low | Claudie Ang | 2015-10-06 | Solved | De Wang | 2015-10-06 | Request.getRequestDispatcher forward message to adminDisplay.jsp
3 | adminDisplay.jsp | Could not direct to servlet from adminDisplay.jsp | high | Miaoqiong | 2015-10-06 | Solved | Fu Yan | 2015-10-06 | response.sendRedirect ("Servlet Name") instead of "Servlet.java".
3 | BootstrapValidation.java | Error Message displayed as "Ling number" | low | Miaoqiong | 2015-10-06 | Solved | Fu Yan | 2015-10-06
3 | BoostrapValidation.java | Email validation could not check for "xxx2014@school.smu.edu.sg" | low | Claudie Ang | 2015-10-06 | Solved | Fu Yan | 2015-10-06 | Check for the dot location in email format
3 | BootstrapValidation.java | Could not check for invalid date format (YYYY-MM-DD) | high | Miaoqiong | 2015-10-06 | Solved | Miaoqiong | 2015-10-06
3 | adminDisplay.jsp | Could not filter not other file types and display error message. | high | Claudie Ang | 2015-10-07 | Solved | Miaoqiong | 2015-10-07 | form accept = ".zip" file.getContentType().equals("application/octet-stream")
3 | adminDisplay.jsp BootstrapServlet.java | Upload file repository created in C drive, project clean build could not clear the C drive repository | high | Claudie Ang | 2015-10-07 | Solved | Fu Yan | 2015-10-07 | Changed file directory to project app folder
3 | Update.jsp UpdateServlet.java | Did not create another file directory for file unzip | low | Miaoqiong | 2015-10-07 | Solved | Miaoqiong | 2015-10-07
3 | DAOs | Upload to data base could not load finish (takes too long) | Critical | Claudie Ang | 2015-10-08 | Solved | Fu Yan | 2015-10-08 | Upload to database by batch (1000)
3 | ConnectionManager.java | Could not upload Chinese / Japanese / Korean characters onto SQL DB. It appears as codes. | high | Miaoqiong | 2015-10-08 | Solved | Miaoqiong | 2015-10-08 | Added UTF8 character settings to connection manager.
3 | BootstrapServlet.java | Error when used request dispatched and response.sendRedirect() | low | Claudie Ang | 2015-10-08 | Solved | Fu Yan | 2015-10-08
BUG Metrics
58 Points
Formula: 1 x 13 (low) + 5 x 7 (high) + 10 x 1 (critical)

## Iteration 4
BUG LOG
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
4 | appusageDao | retrieve from database, nothing return | low | DEWANG | 2015-10-09 | Solved | DEWANG | 2015-10-09 | sql statement wrong
4 | processBasicAppUsage.java | display wrong percentage | low | DEWANG | 2015-10-09 | Solved | Claudie | 2015-10-09
4 | processBasicAppUsage.java | incorrect user categoried (intense as mild) | low | DEWANG | 2015-10-09 | Solved | Claudie | 2015-10-09
4 | Project JAR Library | Library and JAR files could not be loaded on Openshift | Critical | Fu Yan | 2015-10-11 | Solved | Claudie Ang | 2015-10-11 | Put into WEB/INF folder
4 | Openshift DATA Directory | Could not find Openshift DATA Directory and file directory could not be found with slash "\\" | Critical | Fu Yan | 2015-10-11 | Solved | Claudie Ang | 2015-10-11 | Openshift data directory use "OPENSHIFT_DATA_DIR" Use file.seperator()
4 | processDiuranl.java/ processBasicAppUsage.java/ processAppCagegory | can not get parameter from jsp page | low | Gao Shuang | 2015-10-11 | Solved | De Wang | 2015-10-11
4 | processBasicAppUsage.java | JDK version incompatible | low | Gao Shuang | 2015-10-11 | Solved | De Wang | 2015-10-11 | JDK 7
4 | processAppCategory.java | JDK version incompatible | low | Gao Shuang | 2015-10-11 | Solved | De Wang | 2015-10-11 | JDK 7
4 | processDiurnal.java | JDK version incompatible | low | Gao Shuang | 2015-10-11 | Solved | De Wang | 2015-10-11 | JDK 7
4 | processDiurnalandAppcategory.java | user want to generate app report, but direct to diurnal page | low | Gao Shuang | 2015-10-11 | Solved | De Wang | 2015-10-11
4 | basicAppUsageReport.jsp | user didn’t enter any information, NullpointerException | high | Fu Yan | 2015-10-11 | Solved | Claudie Ang | 2015-10-17
4 | processDiurnal.java | display result not accurate | low | Fu Yan | 2015-10-11 | Solved | De Wang | 2015-10-17
4 | processDiuranl.java/ processBasicAppUsage.java/ processAppCagegory | incorrect user of sendRedirect | low | Fu Yan | 2015-10-11 | Solved | De Wang | 2015-10-11
4 | processSmartphoneOveruse.java/ AppUsageDAO.java/ UserAppUsage.java | Total usage time has infinite decimal places after divided by number of days | low | DEWANG | 2015-10-20 | Solved | Fuyan | 2015-10-20
4 | AppUsageDAO.java | User without usage of smartphone return bug of total time taken | low | Claudie Ang | 2015-10-20 | Solved | Fuyan | 2015-10-20
4 | AppUsageDAO.java | Number of hours during selected dates calculated wrongly | low | Claudie Ang | 2015-10-20 | Solved | Fu Yan | 2015-10-20
4 | processSmartphoneOveruse.java | Startdate after enddate lead to error page | low | Claudie Ang | 2015-10-20 | Solved | Gao Shuang | 2015-10-20
4 | processSmartphoneOveruse.java | Empty startdate and enddate lead to error page | low | Tian DeWang | 2015-10-20 | Solved | Gao Shuang | 2015-10-20
4 | AppUsageDAO.java/ UserAppUsage.java | Method used to count number of sessions per hour wrong | low | Fu Yan | 2015-10-20 | Solved | Fu Yan | 2015-10-20
4 | processTopkSchool.java processTopkStudent.java processTopkUsageReport.java | Top K Usage report, user does not put start date and end date, but put K-Value and Filter | low | De Wang | 2015-10-22 | Solved | De Wang | 2015-10-22
4 | processTopkSchool.java processTopkStudent.java processTopkUsageReport.java | Top K Usage Report, user select start date and end date and other filters, but result set is less than K-Value selected. Will have blank row at the end of display | low | De Wang | 2015-10-22 | Solved | De Wang | 2015-10-22
4 | processTopkSchool.java processTopkStudent.java processTopkUsageReport.java | Top K Usage Report, if there are records with same ranking, user K-Value does not match number of records displayed | low | De Wang | 2015-10-22 | Solved | De Wang | 2015-10-22
BUG Metrics
44 Points > 10 Stop current development and resolve the bug immediately.
Formula: 1 x 19 (low) + 5 x 1 (high) + 10 x 2 (critical)

## Iteration 5
Iteration | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
5 | processBasicAppUsage.java | Cannot retrieve cca data from data base | high | Miao Qiong | 2015-10-26 | Solved | Miao Qiong | 2015-10-26
5 | processBasicAppUsage.java basicAppUsageResult.jsp | CCA record displayed not according to alphabetical order. | low | Miao Qiong | 2015-10-26 | Solved | Miao Qiong | 2015-10-26
5 | BootstrapValidation.java | Could not upload data according the random header sequence | high | Claudie Ang | 2015-10-26 | Solved | Claudie Ang | 2015-10-26
5 | BootstrapValidation.java | Input dataV2.zip without CCA row causes "ArrayIndexOutofBound" | Critical | Tian DeWang | 2015-10-26 | Solved | Tian DeWang | 2015-10-26
5 | basicDirunalReport.java basicUseTimeReport basicUseTimeDemographicsReport | JSON: Token validation checks not part of common validation | low | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicAppCategoryReport.java basicDiurnalPatternReport.java basicUserTimeDemoReport.java basicUserTimeReport.java topkmostusedapps.java topkmostusedschools.java topkmostusedstudents.java JsonSmartphoneOveruse.java | JSON: date validity check is inaccurate. Input: “2015-04-asd” detected as valid date | low | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicDiurnalPatternReport.java | JSON basic diurnal: genderfilter as ‘M’ returns nullpointerexception | high | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | JSON files | Not case-insenstive | low | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicUserTimeDemoReport.java | running json without any fields produces null pointer exception | high | Gao Shuang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicAppCategoryReport.java | percentage values not rounded up [JSON output fixed] | low | Gao Shuang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicAppCategoryReport.java | Category names not lowercase | low | Gao Shuang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | authenticate.java | User password should be case sensitive | low | Gao Shuang | 2015-11-03 | Solved | Claudie Ang | 371029
5 | basicUserTimeReport.java | results => [percentage not displayed as ‘mild-percent’, ‘intense-percent’] | low | Gao Shuang | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | basicDiurnalPatternReport.java | GenderFilter, yearFilter, schoolFilter should be optional. If no values to be filtered, JSON should detect filter value as "NA". | low | Tian DeWang | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | basicDiurnalPatternReport.java | null pointer exception with no input fileds | high | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | basicDiurnalPatternReport.java | Last time slot not [23:00 - 00:00] | low | Tian DeWang | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | topkmostusedapps.java topkmostusedschools.java topkmostusedstudents.java | start date and end date should be displayed as “startdate” & “enddate” instead | low | Fu Yan | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | topkmostusedapps.java topkmostusedschools.java topkmostusedstudents.java | White space trimming issues. With double white space. | low | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | JsonSmartphoneOveruse.java | not alphabetical order / start date end date should be startdate and enddate | low | Fu Yan | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | JsonSmartphoneOveruse.java | Nullpointerexception generated when fake Mac address entered(but valid SHA-1 format) | high | Tian DeWang | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | JsonSmartphoneOveruse.java | “invalid mac-address” is incorrect. Should be “invalid macaddress” | low | Tian DeWang | 2015-11-03 | Solved | Wang Miaoqiong | 2015-11-03
5 | basicUserTimeDemoReport.java basicUserTimeReport.java | Not all outer arrays sorted by ascending order (i.e. when gender/year is selected, M is displayed before F) | low | Tian DeWang | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | topkmostusedapps.java topkmostusedschools.java topkmostusedstudents.java | "invalid school name” is incorrect, should be displayed as “invalid school" | low | Fu Yan | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | topkmostusedapps.java topkmostusedschools.java topkmostusedstudents.java | “blank K value” should be displayed as “blank k” “invalid K value” should be displayed as “invalid k” | low | Fu Yan | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | topkmostusedstudents.java | “invalid appcategory name” should be displayed as “invalid app category” | low | Fu Yan | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | topkmostusedschools.java topkmostusedstudents.java | valid startdate 2015-04-06 produces the message “invalid start date” | high | Fu Yan | 2015-11-03 | Solved | Claudie Ang | 2015-11-03
5 | Bootstrap.java Update.java Unzip.java | uploading a .DS_Store got FileNotFoundException | high | Gao Shuang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
5 | Bootstrap.java Update.java | Error message format is wrong [Should not be “Message” : ] | low | Gao Shuang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
5 | Bootstrap.java Update.java | ArrayIndexOutOfBoundsException when zip file does not contain cca | high | Gao Shuang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
5 | Bootstrap.java Update.java | Admin token not validated Normal user token can JSON bootrstrap | high | Gao Shuang | 2015-11-04 | Solved | Gao Shuang | 2015-11-04
BUG Metrics
79 Points > 10 Stop current development and resolve the bug immediately.
Formula: 1 x 19 (low) + 5 x 10 (high) + 10 x 1 (critical)

## Iteration 6
Test Case (UAT) | Files Affected | Description | Severity | Discovered By | Date Discovered | Status | Resolved By | Resolve Date | Remarks
UAT TC 5,6,7 | ProcessBasicAppUsage.java | Access basic app usage report will redirect to login page due to exception | Critical | UAT (Week 13) | 2015-11-07 | Solved | Claudie Ang | 2015-11-09 | Handle the NullPointerException
UAT TC 11 | ProcessBasicAppCategory.java UserAppUsage.java | Value displayed for basic app usage report breakdown by app category is wrong: Expected: (Social: 600 (89%) Education: 78 (11%) ) Ours: (Social: 602, (89%) Education: 77, (11%)) | Low | UAT (Week 13) | 2015-11-07 | Solved | Tian DeWang | 2015-11-09 | Usage time calculation method changed
UAT TC 12 | ProcessDiurnal.java UserAppUsage.java | Value displayed for basic app usage diurnal report is wrong: Expeceted: 23:00 - 00:00: 545 22:00 - 23:00: 98 Ours: 23:00 - 00:00: 1200 22:00 - 23:00: 98 | Low | UAT (Week 13) | 2015-11-07 | Solved | Tian DeWang | 2015-11-09 | Usage time calculation method changed
UAT TC 13 | ProcessDiurnal.java UserAppUsage.java | Value displayed for basic app usage diurnal report is wrong: Expeceted: 23:00 - 00:00: 1090 22:00 - 23:00: 5 Ours: 23:00 - 00:00: 1200 22:00 - 23:00: 5 | Low | UAT (Week 13) | 2015-11-07 | Solved | Tian DeWang | 2015-11-09 | Usage time calculation method changed
UAT TC 15 | ProcessTopkUsageReport.java TopkUsage.java | Value displayed for Topk most used app report is wrong: Expected: Rank 1: Telegram V2: 600 WhatsApp V2: 600 Facebook V2: 600 Ours: Facebook V2 MISSING | High | UAT (Week 13) | 2015-11-07 | Solved | Tian DeWang | 2015-11-09 | Usage time calculation method changed
UAT TC 17,18,21 | ProcessSmartphoneOveruse.java | Value displayed for Smartphone OveruseReport is wrong: Expected: TC 17: (720) (0) TC 18: (792) (0) TC 21: (793) (10) Ours: TC 17: (720.00) (0.00) TC 18: (792.00) (0.00) TC 21: (793.00) (10.00) Usage time (seconds) should not display in 2 decimal places | Low | UAT (Week 13) | 2015-11-07 | Solved | Gao Shuang | 2015-11-09 | Usage time calculation method changed
UAT TC: 37 | BootstrapValidation.java | Bootstrap Validation does not match project requirement: Expected: app.csv Line 10,11,12 "invalid timestamp" app.csv Line 13 "invalid app" app.csv Line 14 "invalid macaddress" app-lookup.csv Line 7: blank app-name, blank app-id app-lookup.csv Line 8: invalid app-id Ours: app.csv Line 10,11,12 "Invalid date format" app.csv Line 13: "Invalid app-id" app.csv Line 14: "No matching mac address, invalid macaddress" app-lookup.csv Line 7: Blank [app-id]. Missing “blank [app-name] app-lookup.csv Line 8: Missing Error Message and uploaded (appid > 0) | high | UAT (Week 13) | 2015-11-07 | Solved | Fu Yan | 2015-11-09 | BootstrapValidation.java changes: 1. Blank error message will add in all blank fields and return 2. Error message changes: invalid date format => invalid timestamp invalid app-id (app.csv) => invalid app 3. app.csv if macaddress is not valid, no need to check for matching macaddress 4. app-id validataion in app-lookup.csv, changed to "validate positive non-zero integer value" (appid > 0)
UAT (JSON) Automated Checked TC: 2, 17, 18, 21 | Bootstrap.java Update.java | Bootstrap: 1. "CCA" should be "cca" 2. error message file name should be "demgraphics.csv" instead of "demogrhics.csv" 3. error message file name should be "app-loopup.csv" instead of "applookup.csv" 4 line number in error message should be interger, not a string 5. filename should contains no space 6. error message should be "invalid timestap" not "invalid time stamp" | Low | UAT Automated Checker | 2015-11-10 | Solved | Wang MiaoQiong | 2015-11-11 | Make changes to JSON message closely following project requirements
UAT (JSON) Automated Checked TC: 6,7 | basicUseTimeDemoReport.java | Basic use time demographics report: 1. If startdate input is the same as enddate JSON validate as invalid | Low | UAT Automated Checker | 2015-11-10 | Solved | Claudie Ang | 2015-11-11 | Change enddate String from: date + 00:00:00 to date + 23:59:59
UAT (JSON) Automated Checked TC: 9 | UserAppUsage.java | Basic app usage breakdown by app category: App usage calculation wrong. (Refer to UAT TC: 11 This affects JSON output as well. | Low | UAT Automated Checker | 2015-11-10 | Solved | Tian DeWang | 2015-11-11 | Usage time calculation method changed
UAT (JSON) Automated Checked TC: 10, 11 | UserAppUsage.java | Basic app usage diurnal report: App usage calculation wrong. (Refer to UAT TC: 12, 13 This affects JSON output as well. | Low | UAT Automated Checker | 2015-11-10 | Solved | Tian DeWang | 2015-11-11 | Usage time calculation method changed
UAT (JSON) Automated Checked TC: 13 | TopkUsage.java | Top K most used app report: App usage calculation wrong. (Refer to UAT TC: 15 This affects JSON output as well. | Low | UAT Automated Checker | 2015-11-10 | Solved | Tian DeWang | 2015-11-11 | Usage time calculation method changed
UAT (JSON) Automated Checked TC: 14 | topkmostusedschool.java | Top K Schools with Most Used App: Wrong JSON output: Expected: "rank" :1, "school":"sis", "duration":1920 Ours: "rank" :1, "school":"sis", "duration":1920 "rank": 2, "school":"law" "duration":0 | Low | UAT Automated Checker | 2015-11-10 | Solved | Tian DeWang | 2015-11-11 | Change JSON display condition: if total usage time is more than zero then display
UAT (JSON) Automated Checked TC: 15,16, 19 | JsonSmartphoneOveruse.java | Smarohone JSON wrong output: Expected: "usage-duration" : 720 "gaming-duration" : 0 "accessfrequency" : 3.0 Ours: "usage-duration" : "720" "gaming-duration" : "0" "accessfrequency" : 3.00 | Low | UAT Automated Checker | 2015-11-10 | Solved accessfrequency is expected in 1dp which is different from wiki requirements so nvr changed | Gao Shuang | 2015-11-11 | Change the result for duration and gaming duration from string to integer format.
BUG Metrics
31 Points > 10 Stop current development and resolve the bug immediately.
Formula: 1 x 11 (low) + 5 x 2 (high)+1x10(critical)