## Slide 1: Final Presentation
G2T2
Ang Claudie
Fu Yan
Gao Shuang
Tian Dewang
Wang Miaoqiong

## Slide 2: agenda
Schedule
Metrics
Use of GIT
Others

## Slide 3: Schedule (Planned V.S. Actual)
11Sep
to 24Sep
25Sep
to 8Oct
ITERATION
Start
1
2
3
11Sep
to 24Sep
25Sep
to 9Oct
Start
1
2
3
Planned
Actual
27Aug
to 10Sep
27Aug
to 3Sep
ITERATION
Schedule
Metrics
Use of Git
Others
Milestone1
22Sep
Supervisor meeting1
Milestone2
30Sep PM review

## Slide 4: Schedule (Planned V.S. Actual)
9Oct
to 22Oct
23Oct
to 5Nov
6Nov
to 18Nov
ITERATION
4
5
6
End
9Oct
to 22Oct
23Oct
to 5Nov
4
5
6
End
Planned
Actual
ITERATION
Schedule
Metrics
Use of Git
Others
Milestone3
13Oct
Supervisor meeting2
Milestone4
27Oct
Supervisor meeting3
Milestone5
3Nov UAT
Milestone6
18Nov
Final presentation
Milestone5
7Nov UAT
Milestone6
19Nov
Final presentation
6Nov
to 15Nov

## Slide 5: Functionalities (BLUE)
No dropping/addition of functionalities
  Login
  Bootstrap
  Basic App Usage Report
  Top-k App Usage Report
  Smartphone Overuse Report
  Dual Interfaces (Web UI and Web Services)
Model View Controller(MVC)
Schedule
Metrics
Use of Git
Others

## Slide 6: External Libraries
Schedule
Metrics
Use of Git
Others
Library Name | Description
fileupload | Multipart form upload processing
gson-2.3 | Java library to convert java object into JSON representation.
is203-jwt-v2 nimbus-jose-jwt-2.26.1 json-smart-1.2 | Generate/verify token for web services. JSON API
opencsv-3.5 | Reading and writing CSV in Java
uploadbean | Allows to upload files from browser
mysql-connector-java-5.1.23-bin | SQL commands

## Slide 7: task allocation
Programming | Non Programming
Login Bootstrap Basic App Usage Report Top-k App Usage Report Smartphone Overuse Report Dual Interfaces (Web UI and JSON) Integration Testing and debugging | Diagrams Design (SD, use case, etc.) Review and update diagrams Test case design/ update Deploy to Openshift PM Tasks (metrics collection, code sharing, etc.)
Schedule
Metrics
Use of Git
Others

## Slide 8: Iteration 1
Schedule
Metrics
Use of Git
Others
PM: Claudie | 
Tasks | Assigned to
Assignment of roles and tasks | Claudie
Project preparation( access scope & read requirements) | Claudie
Draw use case diagram | Claudie
Write use case scenario | Claudie

## Slide 9: Iteration 2
Schedule
Metrics
Use of Git
Others
PM: Claudie | 
Tasks | Assigned to
Draw Sequence diagram for bootstrap | Gaoshuang, Miaoqiong
Draw Sequence diagram for Login | Claudie, Dewang
Coding for Login | Claudie, Dewang
Coding for Login | Gaoshuang, Miaoqiong
Draw Class Diagram | Claudie, Dewang
Draw Logical Diagram | FuYan, Dewang
Draw Sequence Diagram (Basic app) | Claudie, Dewang
Draw Sequence Diagram (Smartphone) | Miaoqiong,FuYan
Draw Sequence Diagram (Top-k) | Miaoqiong, Gaoshuang

## Slide 10: Iteration 2
Schedule
Metrics
Use of Git
Others
PM: Claudie | 
Tasks | Assigned to
Preparation for Supervisor meeting | Claudie
Test case design | FuYan
Update use case/ SD/CD | Claudie
Coding for Login | Miaoqiong, Gaoshuang
Code Sharing | Claudie
Metric collection and mitigation | Claudie
PM handover | Claudie
Update next iteration schedule | Claudie

## Slide 11: Iteration 3
Schedule
Metrics
Use of Git
Others
PM: Dewang | 
Tasks | Assigned to
Test case design for bootstrap | Claudie,Gaoshuang
Test case design (basic app usage) | FuYan, Dewang
Update Use case diagrams/SC/CD | Fuyan, Miaoqiong
Common validation & file specific validation | Gaoshuang, FuYan
Unzip files | Miaoqiong, Dewang
Upload data | Miaoqiong, Dewang
Read CSV and additional data | Claudie,FuYan
Testing and debugging (Login) | Gaoshuang, Miaoqiong
Basic app usage report by app category | Claudie, FuYan

## Slide 12: Iteration 3
Schedule
Metrics
Use of Git
Others
PM: Dewang | 
Tasks | Assigned to
Basic app usage report by useage time category; usagetimecategory+demographics | Claudie, Dewang
Diurnal pattern of app usage time | Claudie, Dewang
Testing & debugging (app usage report) | Claudie, Dewang
Testing & debugging (bootstrap) | Miaoqiong, Claudie
Testing & debugging after integration | Claudie, Miaoqiong
Deploy function to Openshift | Dewang
Integrating with earlier functionalities | FuYan, Dewang
Testing and debugging on openshift | Gaoshuang

## Slide 13: Iteration 3
Schedule
Metrics
Use of Git
Others
PM: Dewang | 
Tasks | Assigned to
Code Sharing | Dewang
Metric collection and mitigation | Dewang
PM handover | Dewang, Gaoshuang
Update next iteration schedule | Dewang

## Slide 14: Iteration 4
Schedule
Metrics
Use of Git
Others
PM: Gaoshuang | 
Tasks | Assigned to
Integrating with earlier functionalities | Gaoshuang, Miaoqiong
Optimize bootstrap performance | FuYan, Miaoqiong
Testing & debugging app usage report | Gaoshuang, Dewang
Test Case design (smartphone) | Dewang, Gaoshuang
Test Case design (top-k) | Gaoshuang, Miaoqiong
Deploy function to openshift | Claudie, Dewang
Testing and debugging on openshift | FuYan, Gaoshuang
Coding for smartphone overuse report | FuYan, Gaoshuang
Prepare for supervisor meeting | Gaoshuang

## Slide 15: Iteration 4
Schedule
Metrics
Use of Git
Others
PM: Gaoshuang | 
Tasks | Assigned to
Coding for Top-k usage report | Dewang Miaoqiong
Testing & debugging for top-k usage report | Gaoshuang, Miaoqiong
Testing & debugging for (smartphone) | FuYan, Dewang
Update use case diagrams/SC/CD | FuYan, Miaoqiong
Deploy top-k function to openshift | Dewang, Miaoqiong
Deploy smartphone function to openshift | FuYan, Gaoshuang
Integrating smartphone, top-k with earlier functions | Gaoshuang, Dewang
Testing and debugging on openshift (smartphone) | FuYan, Claudie
Testing and debugging on openshift (top-k) | Miaoqiong, Dewang

## Slide 16: Iteration 4
Schedule
Metrics
Use of Git
Others
PM: Gaoshuang | 
Tasks | Assigned to
Code Sharing | Gaoshuang
Further edit top-k and Smartphone diagrams | FuYan, Miaoqiong
Metric collection and mitigation | Gaoshuang
PM handover | FuYan Gaoshuang
Update next iteration schedule | Gaoshuang, FuYan

## Slide 17: Iteration 5
Schedule
Metrics
Use of Git
Others
PM: FuYan | 
Tasks | Assigned to
Update use case/SD (project requirement changes) | Miaoqiong
Update test cases (project requirement changes) | FuYan
Coding for Basic App usage report (project requirements changes) | Claudie, Dewang
Coding for Bootstrap (project requirement changes) | Miaoqiong, Gaoshuang
Testing & debugging (basic app, requirement changes) | Gaoshuang, Miaoqiong
Testing & debugging (bootstrap, requirement changes) | Claudie, Dewang
Deploy app to openshift | Miaoqiong
Integration with earlier functions, testing & debugging | FuYan, Dewang
Testing & debugging App on openshift | Gaoshuang, Dewang

## Slide 18: Iteration 5
Schedule
Metrics
Use of Git
Others
PM: FuYan | 
Tasks | Assigned to
Test case design for dual interface | Gaoshuang, Dewang
Update use case/SD for dual interface | Claudie
Coding (Json) | Claudie, Miaoqiong
Coding (Web UI) | Dewang, Gaoshuang
Integrating with earlier functions | Gaoshuang, FuYan
Testing & debugging (dual interface) | FuYan, Dewang
Testing & debugging on dual interface(after integration, local testing) | Gaoshuang, Dewang
Deploy app to openshift | Miaoqiong, Dewang
Testing & debugging on openshift | Gaoshuang, FuYan

## Slide 19: Iteration 5
Schedule
Metrics
Use of Git
Others
PM: FuYan | 
Tasks | Assigned to
Code Sharing | FuYan
Further edit top-k and Smartphone diagrams | FuYan, Miaoqiong
Metric collection and mitigation | FuYan
PM handover | FuYan, Miaoqiong
Update next iteration schedule | Miaoqiong, FuYan

## Slide 20: Iteration 6
Schedule
Metrics
Use of Git
Others
PM: Miaoqiong | 
Tasks | Assigned to
Final testing & debugging (smartphone & bootstrap) | FuYan, Dewang
Final testing & debugging (top-k) | FuYan, Dewang
Update and finalize all technical documents | Claudie, Gaoshuang
Final testing and debugging (Json) | FuYan, Gaoshuang
Final testing & debugging (basic app & json) | Claudie, Miaoqiong
Finalizing final presentation slides | Miaoqiong
Metric collection | Miaoqiong
Preparation of final presentation slides | FuYan, Dewang
Code Sharing | Miaoqiong
Presentation rehearsal | Miaoqiong

## Slide 21: task allocation
Schedule
Metrics
Use of Git
Others
Chart: Non programming hour
| Miaoqiong | Dewang | Gaoshuang | FuYan | Claudie
Series 1 | 20.5 | 17 | 20 | 20 | 21

## Slide 22: task allocation (Non-Programming)
Schedule
Metrics
Use of Git
Others
Chart: 
| Miaoqiong | Dewang | Gaoshuang | FuYan | Claudie
hour | 0.20812 | 0.17259 | 0.20305 | 0.20305 | 0.2132

## Slide 23: task allocation
Schedule
Metrics
Use of Git
Others
Chart: Programming hour
| Miaoqiong | Dewang | Gaoshuang | FuYan | Claudie
Series 1 | 60.92 | 60.88 | 59.81 | 61.42 | 61.32

## Slide 24: task allocation (programming)
Schedule
Metrics
Use of Git
Others
Chart: 
| Miaoqiong | Dewang | Gaoshuang | FuYan | Claudie
hour | 0.20016 | 0.20003 | 0.19652 | 0.20181 | 0.20148

## Slide 25: task allocation
Schedule
Metrics
Use of Git
Others
Chart: Programming hour/Non-programming hour
| Miaoqiong | Dewang | Gaoshuang | FuYan | Claudie
Programming | 60.92 | 60.88 | 59.81 | 61.42 | 61.32
Non-Programming | 20.5 | 17 | 20 | 20 | 21

## Slide 26: SCHEDULING Problems encountered
Inaccurate time estimation
  Learn from previous iterations
  Discuss with coders
Unequal work distribution
  Reallocation of work done by each member
Lab test and other modules deadline
  Avoid scheduling major task during these periods
Schedule
Metrics
Use of Git
Others

## Slide 27: Task Metric
Iteration | Plan | Actual | Score | Action
1 | 4 | 4 | 1 | No actions required
2 | 17 | 17 | 1 | No actions required
3 | 21 | 16 | 0.77 | Re-estimate the tasks for the future iterations. Deduct the number of days behind schedule from buffer days. If there is no more buffer day, decide the functionalities to drop.
4 | 23 | 23 | 1 | No actions required
5 | 22 | 22 | 1 | No actions required
6 | 11 | 11 | 1 | No actions required
Schedule
Metrics
Use of Git
Others

## Slide 28: Pair Programming Metric Iteration 2
Task | Plan | Actual | Score | Action
Login Database Connection | 1 | 0.93 | 1.07 | No action required.
Login Testing & Debugging | 1 | 1.13 | 0.88 | No action required.
Unzip file | 1 | 3.2 | 0.31 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
Common validation | 3 | 3.17 | 0.95 | No action required.
Schedule
Metrics
Use of Git
Others

## Slide 29: Pair Programming Metric Iteration 3
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Upload data | 1 | 2.48 | 0.4 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
Read csv and add additional data | 2 | 2.7 | 0.74 | No action required.
Basic app usage report breakdown by usage time/usage time + demographics | 6.25 | 7.78 | 0.8 | No action required.

## Slide 30: Pair Programming Metric Iteration 3
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Basic app usage report breakdown by app category | 5 | 7.25 | 0.69 | No action required.
Diurnal pattern of app usage | 3.5 | 6.12 | 0.57 | No action required.
Testing & Debugging for login | 1 | 1.13 | 0.88 | No action required.
Testing & debugging for bootstrap | 5.5 | 11 | 0.5 | No action required.
Testing & debugging for app usage report | 2 | 2.18 | 0.92 | No action required.

## Slide 31: Pair Programming Metric Iteration 4
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
integrating with earlier functionalities | 1 | 8.8 | 0.11 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
optimize bootstrap performance | 6 | 5.08 | 1.18 | No action required.
Testing & debugging app usage report | 2 | 3.7 | 0.54 | No action required.
testing and debugging on openshift | 4 | 5.5 | 0.73 | No action required.
Coding for Smartphone Overuse Report | 10 | 8.2 | 1.22 | No action required.

## Slide 32: Pair Programming Metric Iteration 4
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Coding for Top-k Usage Report | 15 | 5.67 | 2.65 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. 2. Review possible pairing & estimation issues.
Testing & Debugging for Smartphone Overuse Report | 2 | 3.27 | 0.61 | No action required.
Testing & Debugging for Top-k Usage Report | 4 | 3.63 | 1.10 | No action required.
Integrating & testing Top-k Report and Smartphone Overuse Report with earlier functionalities | 1 | 1.58 | 0.63 | No action required.

## Slide 33: Pair Programming Metric Iteration 4
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Testing & Debugging Smartphone Overuse Report on OpenShift | 2.95 | 2 | 1.48 | No action required.
Testing & Debugging Top-k Usage Report on OpenShift | 2 | 0.75 | 2.67 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. 2. Review possible pairing & estimation issues.

## Slide 34: Pair Programming Metric Iteration 5
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Coding for Basic App Usage Report (project requirement changes) | 8 | 8.32 | 0.96 | No action required.
Coding for Bootstrap (project requirement changes) | 3 | 2.42 | 1.24 | No action required.
Testing and Debugging for Bootstrap (project requirement changes) | 2 | 1.57 | 1.28 | No action required.
Testing and Debugging for Basic App Usage Report (project requirement changes) | 2 | 2.2 | 0.91 | No action required.

## Slide 35: Pair Programming Metric Iteration 5
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Integration with earlier functions. Test and Debugging after integration(project requirement changes) | 3 | 2.92 | 1.03 | No action required.
Testing and Debugging App on OpenShift | 2 | 1.25 | 1.6 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. 2. Review possible pairing & estimation issues.
Coding (JSON) | 8 | 8.9 | 0.9 | No action required.
Coding (Web UI) | 2 | 2.68 | 0.75 | No action required.
Integrating with earlier functionalities | 2 | 1.47 | 1.36 | No action required.

## Slide 36: Pair Programming Metric Iteration 5
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Testing and Debugging on Dual Interface Features (local testing) | 2 | 2.38 | 0.84 | No action required.
Testing and Debugging of Dual Interfaces (After integration, local testing) | 2 | 2.55 | 0.78 | No action required.
Testing and Debugging on Openshift | 2 | 1.82 | 1.1 | No action required.

## Slide 37: Pair Programming Metric Iteration 6
Schedule
Metrics
Use of Git
Others
Iteration 2
Task | Plan | Actual | Score | Action
Final testing and debugging (bootstrap & smartphone) | 2 | 2.83 | 0.71 | No action required.
Final testing and debugging (top-k) | 2 | 1.83 | 1.09 | No action required.
Final testing and debugging | 2.5 | 2.27 | 1.10 | No action required.
Final testing and debugging (basic app & json) | 4 | 4.73 | 0.85 | No action required
Integrating and finalizing app | 1 | 1.98 | 0.51 | No action required

## Slide 38: BUG Metric –overview
Schedule
Metrics
Use of Git
Others
Iteration 2
Iteration | Low | High | Critical | Total
3 | 13 | 7 | 1 | 58
4 | 19 | 1 | 2 | 44
5 | 19 | 10 | 1 | 79
6 | 11 | 2 | 10 | 31
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Slide 39: Metrics Problems encountered
Difficulty with time estimation
  Learn from previous iterations and assess functions workload carefully
Unfamiliar with all the metrics
  Clarify with PPT Slides. Study and understand all metrics.
Pairing the programmers to ensure better task distribution
  Estimate the programming hours and rearrange the pairs
Schedule
Metrics
Use of Git
Others

## Slide 40: task allocation (Non-Programming)
Schedule
Metrics
Use of Git
Others
Chart: Total Numer of commits: 199
| Miaoqiong | Gaoshuang | Claudie | Dewang | FuYan
Total Numer of commits: 198 | 37 | 43 | 23 | 45 | 51

## Slide 41: OUT OF SESSION COMMITS
Schedule
Metrics
Use of Git
Others
S/N | Date | Commit Message
1 | 27/10/2015 18:27 | update latest app
2 | 27/10/2015 12:44 | Merge branch 'master' of green.smu.edu.sg:is203/is203_g2t2
3 | 21/10/2015 16:04 | edit UI for smartphone overuse
4 | 20/10/2015 20:07 | Update for smartphoneOveruseReport
5 | 20/10/2015 20:06 | AppUsageDAO update
6 | 20/10/2015 20:04 | UserAppUsage update
7 | 19/10/2015 18:41 | Merge branch 'master' of green.smu.edu.sg:is203/is203_g2t2
8 | 13/10/2015 18:20 | Merge branch 'master' of green.smu.edu.sg:is203/is203_g2t2
9 | 09/10/2015 22:08 | Update basicAppUsageReportDemo.jsp for jquery unnecessary codes
10 | 04/10/2015 21:10 | update app
11 | 04/10/2015 21:09 | update app
12 | 28/09/2015 18:59 | Merge branch 'master' of green.smu.edu.sg:is203/is203_g2t2
13 | 25/09/2015 12:51 | Added Meeting Minutes according to specified Directory, Added .gitignore file in 'app'

## Slide 42: Takeaways
Project management
Time management
Peer learnings
Team work
Technical and analytical skills
Schedule
Metrics
Use of Git
Others

## Slide 43: Problem resolution
Schedule
Metrics
Use of Git
Others
Unsure how to do some of the functions
  Self-learning outside the class
Motivation
  PM organizes team bonding session
Lack of space in school
  Go to PM’s house

## Slide 44: Something interesting
Schedule
Metrics
Use of Git
Others
Claudie likes to sing “My heart will go on” whenever we find bugs.
Steamboat session every two weeks.
De Wang prepared week 7 ppt slides overnight.
Gao Shuang lives 5 minutes walk from school
Miaoqiong likes to traveling