## Slide 1: Week 11 Supervisor Meeting
Software Engineering
G2T2

## Slide 2: Content
Project Progress (Previous Iterations)
Project Requirement Changes (OH NO!)
Actions Taken
Iteration 5 Updates

## Slide 3: Project Progression
Iteration 1 - 4

## Slide 4: Iteration 1 – 3 (Recap)
Iteration 1
(PM Claudie Ang)
Project Planning
Assign Roles
System Design
Prepare SD, Use Case Diagram
Iteration 2
(PM Claudie Ang)
System Design
Develop Login Function

## Slide 5: Iteration 1 – 3 (Recap)
Iteration 3 (PM Tian De Wang)
Test and Debugging for Login function
Develop Bootstrap / Update Additional Data Functions
Develop Basic App Usage Reports Functions
Integrate and Local Testing and Debugging

## Slide 6: Iteration 1-3 (Recap)
ISSUES:
  Git Repository (App within an App folder)
  Wrong Naming of Files on Git
  (bm.xlsx, ppm.xlsx)
  Work Allocation Is Skewed
  OpenShift URL Wrong
  Login User Name (Email ID instead of Name)

## Slide 7: Iteration 1-3 (Recap)
Actions Taken:
  Fixed GIT Repository
  Changed Naming of Files
  Allocate Claudie minimum work for Iteration 4, while the rest catch up.
  Fixed OpenShift URL
  Update Login Using Email ID

## Slide 8: Iteration 4 Review
PM (Gao Shuang)
Delayed Tasks from Iteration 3
    OpenShift Deployment
    Testing and Debugging on OpenShift
Develop Top K Usage Report
Develop Smartphone Over-use Report
Integration, local Testing and Debugging
OpenShift Deployment
Testing and Debugging on OpenShift

## Slide 9: Iteration 4 Review
Task Metric
Iteration | Plan | Actual | Score | Action
1 | 4 | 4 | 1 | No actions required
2 | 17 | 17 | 1 | No actions required
3 | 21 | 16 | 0.77 | Re-estimate the tasks for the future iterations. Deduct the number of days behind schedule from buffer days. If there is no more buffer day, decide the functionalities to drop.
4 | 23 | 23 | 1 | No actions required

## Slide 10: Iteration 4 Review
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
BUG Metrics | 
41 Points > 10 Stop current development and resolve the bug immediately. | 
Formula: 1 x 16 (low) + 5 x 1 (high) + 10 x 2 (critical) | 

## Slide 11: Iteration 4 Review
Pair Programming Metric

## Slide 12: Iteration 4 Review

## Slide 13: Iteration 4 Review

## Slide 14: Project Requirement Changes
Iteration 5

## Slide 15: Project Requirement Changes
Iteration 5
Demographics.csv adding CCA records
Bootstrap / Upload Additional Data Handling Columns
Basic App Usage Report
  (Break down by usage time category and demographics)
Performance (2 mins 30 s for data v2)

## Slide 16: Project Requirement Changes
Actions Taken
Internal Meeting 23rd OCT 2015
Gather Input on Requirement Changes
Re-estimate Time to Complete the Changes
Re-schedule Iteration 5

## Slide 17: Project Requirement Changes
Iteraion 5 Overview
23-10-2015
    Internal Meeting
    Update Diagrams
    Update Test Cases
24-10-2015 to 25-10-2015
    Develop Bootstrap Changes
    Develop Basic App Usage Report Changes
26-10-2015
    Integration and Testing (Local)
    Deploy and Testing (OpenShift)

## Slide 18: Project Requirement Changes
Iteraion 5 Overview
27-10-2015 to 30-10-2015
    Develop Dual UI (Web and JSON)
30-10-2015
    Integrate and Local Testing (Dual UI)
31-10-2015
    Deployment and Testing on OpenShift
01-11-2015 to 03-11-2015
    Buffer Time (3 days) Reduced (from 7 days previously)
04-11-2015 (11pm)
    Final Deployment for UAT
    UAT (07-11-2015, SAT, 2pm-3:30pm. SIS SR 3-2)

## Slide 19: THE END
THANK YOU!