## Slide 1: SOFTWARE Engineering PM REVIEW
G2 TEAM 2

## Slide 2: content
Functionalities
Schedule
Metrics
Roles & Responsibilities
Pair Programming Rotation Plan

## Slide 3: Functionalities
G2 TEAM2 COLOR: BLUE
Login
Bootstrap
Basic App Usage Report
Top-k App Usage Report
Smartphone Overuse Report
Dual Interfaces (Web UI and Web Services)

## Slide 4: JSP MODEL 1
JSP
(View + Controller)
DataManager
(Model)
Database
1. HTTP Request
Browser
6. HTTP Response
2. Invokes method (CRUD)
Java Class
(Model)
4. Instantiates object (for select)
5. Retrieves data
3. Connects & retrieves data

## Slide 5: Schedule
27Aug
to 10Sep
11Sep
to 24Sep
25Sep
to 8Oct
9Oct
to 22Oct
23Oct
to 5Nov
6Nov
to 18Nov
ITERATION
Start
1
2
3
4
5
6
End
Read Requirements, Assignment of Roles and Task, Use cases
SD, LD, Class diagrams, Login (Test Case + Coding)
Milestone1
22Sep
Supervisor meeting1
Login Debugging, Bootstrap,
App Usage Report
Milestone2
30Sep PM review
Top-k, Smartphone Overuse Report
Milestone3
13Oct
Supervisor meeting2
Web UI and Web Service
Testing before UAT
Milestone4
27Oct
Supervisor meeting3
Milestone5
3Nov UAT
Final code sharing, deployment, testing and Presentation Preparation
Milestone6
18Nov
Final presentation
Buffer Time

## Slide 6: Schedule
DESIGN
INTERNAL MEETING
DEVELOPMENT
LOCAL TEST
INTEGRATION & TESTING
END OF ITERATION
DEPLOYMENT & TESTING

## Slide 7
Iteration 1: ▼ | PM: Claudie
Design | 
Read requirements | Claudie
Assignment of Roles and Tasks | Claudie
Write Use case scenario | Claudie
Draw Use case diagrams | Claudie

## Slide 8
Iteration 2: ▼ | PM: Claudie
Internal Meeting | Claudie
Design | 
Draw all the SDs | PM in charge and we discuss and draw diagrams together as a team
Class diagram | 
Logical diagram | 
Feature Design | 
Update Use Case diagrams/SD/Class Diagrams | Claudie
Test Case Design | Fuyan
Development | 
Coding of Login (JAVA Class) | De Wang, Claudie
Coding of Login (UI, Authentication) | Gao Shuang, Miao Qiong
Coding of Login (Database connection) | Miao Qiong
End of Iteration | Claudie

## Slide 9
Iteration 3: ▼ | PM: DEWANG
Internal Meeting | DEWANG
Feature Design | 
Update Use Case diagrams/SD/Class Diagrams | Fuyan,Miaoqiong
Test Case Design for bootstrap | Claudie, Gaoshuang
Test Case Design for App usage Report | Fuyan, DEWANG
Development | 
bootstrap | Pair programming
App usage report | 
Local Test | 
Testing & debugging (login) | Claudie, Fuyan
Testing & debugging (bootstrap) | Gao Shuang, Miao Qiong
Testing & debugging (app usage report) | DEWANG, Claudie
Integration | 
Integrating with earlier functionalities | De Wang, Fu Yan
Testing & Debugging | Miaoqiong, Claudie

## Slide 10
Deployment | 
Deploy function to OpenShift | De Wang
Testing & Debugging on OpenShift | Gao Shuang
End of Iteration | 
Code-sharing | DEWANG
Metric collection and Mitigation | DEWANG
Update next iteration schedule | DEWANG
PM Handover | DEWANG

## Slide 11
Iteration 4: ▼ | PM: Gao Shuang
Feature Design | 
Update Use Case diagrams/SD/Class Diagrams for Top-k and Smartphone Overuse Report | Gao Shuang
Test Case Design (Top-k Usage Report) | Claudie, Dewang
Test Case Design (Smartphone Overuse Report) | Miaoqiong, Fu Yan
Development | 
Coding for Top-k Usage Report | Miaoqiong, Fu Yan
Coding for Smartphone Overuse Report | Claudie, Dewang
Local Test | 
Testing & Debugging for Top-k Usage Report | Miaoqiong, Fu Yan
Testing & Debugging for Smartphone Overuse Report | Claudie, Dewang

## Slide 12
Integration | 
Integrating Top-k Usage Report with earlier functionalities | Miaoqiong, Fu Yan
Integrating Smartphone Overuse Report with earlier functionalities | Claudie, Dewang
Testing & Debugging | Fu Yan, Miaoqiong
Deployment | 
Deploy Top-k Usage Report to OpenShift | Fu Yan, Miaoqiong
Deploy Smartphone Overuse Report to OpenShift | Claudie, Gao Shuang
Testing & Debugging on OpenShift | Gao Shuang
End of Iteration | 
Code-sharing | Gao Shuang
Metric collection and Mitigation | Gao Shuang
Update next iteration schedule | Gao Shuang
PM Handover | Gao Shuang

## Slide 13
Iteration 5: ▼ | PM: FU YAN
Design | 
Update Use Case diagrams/SD/Class Diagrams for Dual Intereface | Fu Yan
Test Case Design (Dual Interface) | Fu Yan, Gao Shuang
Development | 
Coding for Dual Interface | De Wang, Claudie
Local Test | 
Testing & Debugging for Dual Interface | Miaoqiong, Fu Yan
Integration | 
Integrating with earlier functionalities | Gao Shuang, Claudie
Test | 
Testing & Debugging | Miaoqiong, De Wang
Deployment | 
Deploy function to OpenShift | Claudie
Testing & Debugging on OpenShift | Miaoqiong, Gaoshuang

## Slide 14
End of Iteration | 
Code-sharing | Fu Yan
Metric collection and Mitigation | Fu Yan
Update next iteration schedule | Fu Yan
PM Handover | Fu Yan

## Slide 15
Iteration 6: ▼ | PM: Miao Qiong
Update and finalise all diagrams | Claudie, Gao Shuang
Prepare slides | Fu Yan, De Wang
Code-sharing | Miaoqiong
Presentation Rehearsal | Miaoqiong

## Slide 16: Critical path
File-specific validations
Project preparation
Assign roles and tasks
Technical document
1Day
Login function
1Day
7Days
4Days
Code-sharing and handover
1Day
Common Validations
UI and unzip files
1Days
1Days
4Days
Upload data and add additional
3Days
Update SD and design test case
1Day
App usage Report function
3Days
Any delay on a activity on the critical path impacts the completion date

## Slide 17
Local testing
Integration and Deployment
1Day
Code-sharing and handover
1Day
topK usage report function
Smartphone overuse function
8Days
5Days
3Days
Dual interface
Integration and Deployment
Finalize and buffer time
3Days
2Days
9Days
Code-sharing and handover
Integration and Deployment
2Days
Code-sharing and handover
1Day
1Day
Any delay on a activity on the critical path impacts the completion date
Final testing
3Days
Final testing & debugging
Update and finalize technical documents
6Days
3Days
Prepare slides
3Day
Rehearsal
3Day

## Slide 18: Metrics-task metrics
Actual tasks/ Estimated tasks completed
Mitigation plan:
We finished all the tasks in iteration1 and iteration2
90 < Percentage <= 110
Our estimates are fairly accurate, and we are roughly on track

## Slide 20: Bug metrics
Iteration | Files Affected | Description | Severity
3 | authenticate.jsp | Authentication returns false for all cases | low
3 | UserDAO.java | Cannot load data | high
3 | login.jsp | Error messages cannot be printed out | low

## Slide 21
  Formula: 1 x num (low) + 5 x num (high) + 10 x num (critical)
7 points
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Slide 22: Pair programming metrics
Formula: Estimated PP hours/ actual PP hours (per task)
Task | Plan | Actual | Score | Action
Login Database Connection | 1 | 0.93 | 1.07 | No action required.
Login Testing & Debugging | 1 | 1.13 | 0.88 | No action required.
Unzip file | 1 | 3.2 | 0.31 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
Common validation | 3 | 3.17 | 0.95 | No action required.

## Slide 23
Score(%) | Action
PPM < 50 | Re-estimate the tasks in the coming iteration(s) and update the schedule document. Review possible pairing & estimation issues.
50 < PPM <= 150 | No action required.
150 < PPM | Re-estimate the tasks in the coming iteration(s) ) and update the schedule document. Review possible pairing & estimation issues.
Notes: This is a hide page

## Slide 24: Roles & Responsibilities
ITERATION | PROJECT MANAGER | Milestone
1 | Claudie | 
2 | Claudie | 1
3 | DeWang | 2
4 | Gao Shuang | 3
5 | Fu Yan | 4,5
6 | MiaoQiong | 6

## Slide 25: Pair programming rotation plan
STRONG - WEAK
RANDOM PAIRING

## Slide 26
Functionality |  | Rotation
Bootstrap | Unzip files Common validations for all data files/File-specific Validation Upload data, read csv and add additional data, bootstrap | Miaoqiong & Dewang Gaoshuang & Fuyan Claudie & Dewang
App Usage Report | Usage time/Usage time + demographics App category Diurnal pattern of app usage time | Claudie & Gaoshuang Miaoqiong & Fuyan Gaoshuang & Dewang
Top-k App Usage Report | - | Claudie & Dewang
Smartphone Overuse Report | - | Miaoqiong & Fuyan
Dual Interfaces (Web UI and Web Services) | - | Miaoqiong & Dewang Claudie & Gaoshuang

## Slide 27: Q & A

## Slide 28: Thank you SE ALL THE BEST : )